## Sheet1
Sub service | Sheet
Stormwater investigation for detailed plan area | ST-1
Stormwater investigation for building permit | ST-1
Stormwater investigation for existing properties | ST-1
1D stormwater pipe network modelling | ST-6
Flood investigation (1D-2D overland runoff and pipe modelling) | ST-8
Stormwater pipe network design | storm_pipe-2
Water distribution network modelling | W-1
Water hammer analysis | ham-1
Existing water distribution network investigation | ewdni
Water pipe network design | water_pipe-2
Existing sewer network investigation (gravity and pressure sewer system) | sewer-1
Sewer network modelling | snm-1
Sewer network design | sewer_pipe-2

## ST-1
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 40000 | 5000 | 6000 | 2-3 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
0.5 ha to 1 ha | 40000 | 6000 | 6000 | 2-3 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
1-3 ha | 45000 | 8000 | 6000 | 3-4 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
3-5 ha | 45000 | 10000 | 6000 | 3-4 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
5-10 ha | 55000 | 13000 | 6000 | 4-6 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
10-20 ha | 70000 | 16000 | 6000 | 6-8weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
20-30 ha | 85000 | 20000 | 6000 | 9-12 weeks | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
30-50 ha | 100000 | 25000 | 6000 | 3-4 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
50-75 ha | 125000 | 30000 | 6000 | 4-6 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
75-100 ha | 150000 | 38000 | 6000 | 6-9 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)
>100 ha | 250000 | 50000 | 6000 | Minimum 9 months | 1. Existing Condition Analysis (Landuse, Catchment, Flow network) 2. Proposed Condition Analysis (Landuse, Catchment, Flow network) 3. Flow Calculation 4. Pollution Calculation (Pre and Post) 5. Solution for treatment facility 6. Solution for delay facility 7. Proposed runoff plan 8. Low point mapping using SCALGO 9. Flood analysis for 100 years rain using SCALGO | 1. Detail plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geo reports (if not availble, we use data from SGU) 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) | 1. Stormwater investigation report 2. Stormtac File 3. All maps and drawing (shp file)

## ewdni
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 40000 | 5000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
0.5 ha to 1 ha | 40000 | 6000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
1-3 ha | 45000 | 8000 | 6000 | 3-4 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
3-5 ha | 45000 | 10000 | 6000 | 3-4 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
5-10 ha | 55000 | 13000 | 6000 | 4-6 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
10-20 ha | 70000 | 16000 | 6000 | 6-8weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
20-30 ha | 85000 | 20000 | 6000 | 9-12 weeks | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
30-50 ha | 100000 | 25000 | 6000 | 3-4 months | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
50-75 ha | 125000 | 30000 | 6000 | 4-6 months | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
75-100 ha | 150000 | 38000 | 6000 | 6-9 months | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)
>100 ha | 250000 | 50000 | 6000 | Minimum 9 months | 1. Flow calculation 2. Inleak analysis 3. Capacity checking of existing water network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Analysis for proposed pump 7. Propose feasible solution 8. Cost estimation 9. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point/Number of city to be connected 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA network (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 13. Profile of pipe (dwg) | 1. Investigation PM 2. Plan drawing (pdf)

## ST-6
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 20000 | 5000 | 6000 | 2-3 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
0.5 ha to 1 ha | 20000 | 6000 | 6000 | 2-3 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
1-3 ha | 25000 | 8000 | 6000 | 3-6 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
3-5 ha | 30000 | 10000 | 6000 | 3-6 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
5-10 ha | 35000 | 13000 | 6000 | 6-9 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
10-20 ha | 40000 | 16000 | 6000 | 2-3 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
20-30 ha | 50000 | 20000 | 6000 | 3-4 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
30-50 ha | 60000 | 25000 | 6000 | 4-6 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
50-75 ha | 75000 | 30000 | 6000 | 6-9 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
75-100 ha | 100000 | 38000 | 6000 | 9-12 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
>100 ha | 250000 | 50000 | 6000 | Minimum 1 year | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network

## ST-8
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 40000 | 5000 | 6000 | 3-4 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
0.5 ha to 1 ha | 40000 | 6000 | 6000 | 3-4 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
1-3 ha | 50000 | 8000 | 6000 | 4-8 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
3-5 ha | 60000 | 10000 | 6000 | 4-8 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
5-10 ha | 70000 | 13000 | 6000 | 8-12 weeks | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
10-20 ha | 80000 | 16000 | 6000 | 3-4 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
20-30 ha | 100000 | 20000 | 6000 | 4-5 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
30-50 ha | 120000 | 25000 | 6000 | 5-7 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
50-75 ha | 150000 | 30000 | 6000 | 7-10 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
75-100 ha | 200000 | 38000 | 6000 | 10-12 months | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)
>100 ha | 500000 | 50000 | 6000 | Minimum 1 year | 1. Surface preparation according to development plan 2. Watershed delineation 3. 1D model setup (MIKE URBAN) 4. 2D model setup (MIKE21 FM) 5. 1D-2D coupled model setup 6. Flood mapping and problem identification 7. Solution 8. Comparison of pre & post development scenarios | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries 9. Existing and proposed road surface and elevation | 1. Flood investigation report 2. All maps and drawing (shp file)

## W-1
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 7000 | 5000 | 6000 | 2-3 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
0.5 ha to 1 ha | 10000 | 5000 | 6000 | 2-3 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
1-3 ha | 12000 | 8000 | 6000 | 3-6 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
3-5 ha | 15000 | 8000 | 6000 | 3-6 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
5-10 ha | 18000 | 10000 | 6000 | 6-9 weeks | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
10-20 ha | 18000 | 10000 | 6000 | 2-3 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
20-30 ha | 20000 | 15000 | 6000 | 3-4 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
30-50 ha | 20000 | 15000 | 6000 | 4-6 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
50-75 ha | 22000 | 20000 | 6000 | 6-9 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
75-100 ha | 25000 | 25000 | 6000 | 9-12 months | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network
>100 ha | 28000 | 40000 | 6000 | Minimum 1 year | 1. Watershed delineation 2. 1D Model setup and simulation 3. Identification of flooded manholes, pipes and open channels 4. Solution | 1. Project area 2. Existing and proposed stormwater pipe network including nodes and manholes (shp files) 3. Existing and proposed stormwater management facilities (dwg in 3D) 4. Water level/flow at recipient (optional) 5. Specification of scenarios (return period, development stage etc.) 6. Elevation/DEM/Height model (if not available, we use SCALGO) 7. Geo reports (if not available, we use SGU) 8. Existing/proposed property boundaries | 1. Stormwater network modelling report 2. All maps and drawing (shp file) 3. Profiles for pipe network

## snm-1
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 7000 | 5000 | 6000 | 2-3 weeks | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
0.5 ha to 1 ha | 10000 | 5000 | 6000 | 2-3 weeks | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
1-3 ha | 12000 | 8000 | 6000 | 3-6 weeks | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
3-5 ha | 15000 | 8000 | 6000 | 3-6 weeks | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
5-10 ha | 18000 | 10000 | 6000 | 6-9 weeks | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
10-20 ha | 18000 | 10000 | 6000 | 2-3 months | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
20-30 ha | 20000 | 15000 | 6000 | 3-4 months | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
30-50 ha | 20000 | 15000 | 6000 | 4-6 months | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
50-75 ha | 22000 | 20000 | 6000 | 6-9 months | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
75-100 ha | 25000 | 25000 | 6000 | 9-12 months | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
>100 ha | 28000 | 40000 | 6000 | Minimum 1 year | 1. Preparation of pipe network layout and definition 2. Sewer load calculation 3. Model setup 4. Hydraulic analysis and problem identification 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and manholes 4. Existing sewer network 5. Existing and projected population data 6. Information on existing pump 7. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)

## storm_pipe-2
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 15000 | 5000 | 6000 | 2-3 weeks | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
0.5 ha to 1 ha | 15000 | 6000 | 6000 | 2-3 weeks | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
1-3 ha | 20000 | 8000 | 6000 | 3-6 weeks | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
3-5 ha | 25000 | 10000 | 6000 | 3-6 weeks | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
5-10 ha | 30000 | 13000 | 6000 | 6-9 weeks | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
10-20 ha | 40000 | 16000 | 6000 | 2-3 months | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
20-30 ha | 50000 | 20000 | 6000 | 3-4 months | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
30-50 ha | 65000 | 25000 | 6000 | 4-6 months | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
50-75 ha | 85000 | 30000 | 6000 | 6-9 months | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
75-100 ha | 110000 | 38000 | 6000 | 9-12 months | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
>100 ha | 150000 | 50000 | 6000 | Minimum 1 year | 1. Watershed Impact Analysis 2. Flow calculation 3. Required Flow Capacity Calculation 4. Pipe dimensioning 5. Design and dimension technically feasible solution for treatment facility 6. Design and dimension technically feasible solution for delay facility 7. Design and dimension technically feasible solution for flow transportation facility. 8. Prepare the entire Pipe network in AutoCAD (3D) 9. Conflict checking 10. Prepare pipe profile 11. Preparation of PM 12. Prepare typical section drawings | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network (dwg) 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8.Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) | 1. Pipe network Plan (pdf) 2. Profile layout (PDF) 2. 3D Pipe network Model (DWG) 3. Section Drawing (PDF/DWG) 4. PM
#VALUE!

## water_pipe-2
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 15000 | 5000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
0.5 ha to 1 ha | 15000 | 6000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
1-3 ha | 18000 | 8000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
3-5 ha | 20000 | 10000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
5-10 ha | 25000 | 13000 | 6000 | 6-9 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
10-20 ha | 30000 | 16000 | 6000 | 2-3 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
20-30 ha | 40000 | 20000 | 6000 | 3-4 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
30-50 ha | 55000 | 25000 | 6000 | 4-6 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
50-75 ha | 75000 | 30000 | 6000 | 6-9 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
75-100 ha | 100000 | 38000 | 6000 | 9-12 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM
>100 ha | 125000 | 50000 | 6000 | Minimum 1 year | 1. Flow calculation 2. Pipe dimensioning calculation 3. Prepare pipe network plan drawing 4. Prepare typical section drawing 5. Conflict checking 6. Prepare pipe network profile drawing 7. Preparation of PM | 1. Detailed plan (dwg & pdf) 2. Project boundary (dwg) 3. Property boundaries (dwg) 4. Existing and proposed landuse 4. Elevation/height model/DEM (if not available, we use SCALGO) 5. Geotechnical Investigation report 6. Existing stormwater network 7. Location/area of protected site in project area (if not available, we check in SCALGO) 8. Road layout plan (dwg) 9. Existing LSO Network (dwg) 10. Surface Elevation/3d surface (Existing and Proposed) 11.Existing/ projected Population Data | 1. Pipe network plan drawing (pdf) 2. Pipe network plan 3D (dwg) 3. Typical section (dwg/pdf) 4. Profile (dwg/pdf) 5. PM

## sewer_pipe-2
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 15000 | 5000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
0.5 ha to 1 ha | 15000 | 6000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
1-3 ha | 18000 | 8000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
3-5 ha | 20000 | 10000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
5-10 ha | 25000 | 13000 | 6000 | 6-9 weeks | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
10-20 ha | 30000 | 16000 | 6000 | 2-3 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
20-30 ha | 40000 | 20000 | 6000 | 3-4 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
30-50 ha | 55000 | 25000 | 6000 | 4-6 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
50-75 ha | 75000 | 30000 | 6000 | 6-9 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
75-100 ha | 100000 | 38000 | 6000 | 9-12 months | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM
>100 ha | 125000 | 50000 | 6000 | Minimum 1 year | 1. Flow calculation 2. Pipe dimensioning calculation 3. Choosing of pump (if require) 4. Prepare pipe network plan drawing in 3D 5. Prepare typical section drawing 6. Conflict checking 7. Prepare pipe network profile drawing 8. Preparation of PM | 1. Detail Plan (dwg/Shapefile) 2. Road layout plan 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Approximate length of proposed line (m) 6. Geotechnical Investigation report 7. Existing VA (dwg) 8. LSO Network (dwg) 9. Proposed road surface 10. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 11. Area (Ha) 12. Existing Population Data ((not required if client chooses new area) 13. Projected population data (not required if client chooses existing area) | 1. Pipe network plan drawing (pdf) 2. Pipe network plan (dwg) 3. Typical section (dwg/pdf) 4. PM

## sewer-1
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 7000 | 5000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
0.5 ha to 1 ha | 10000 | 5000 | 6000 | 2-3 weeks | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
1-3 ha | 12000 | 8000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
3-5 ha | 15000 | 8000 | 6000 | 3-6 weeks | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
5-10 ha | 18000 | 10000 | 6000 | 6-9 weeks | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
10-20 ha | 18000 | 10000 | 6000 | 2-3 months | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
20-30 ha | 20000 | 15000 | 6000 | 3-4 months | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
30-50 ha | 20000 | 15000 | 6000 | 4-6 months | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
50-75 ha | 22000 | 20000 | 6000 | 6-9 months | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
75-100 ha | 25000 | 25000 | 6000 | 9-12 months | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)
>100 ha | 28000 | 40000 | 6000 | Minimum 1 year | 1. Flow calculation 2. Inleak analysis (not required if client chooses investigation for new area) 3. Capacity checking of existing sewer network 4. Capacity checking of existing pump 5. Analyze air valve requirements 6. Propose new pump (if required) 7. Pipe dimensioning 8. Propose feasible solution (GIS) 9. Cost estimation 10. Preparation of PM | 1. Area (Ha) 2. Detail Plan (dwg/Shapefile) (not required if client chooses investigation for existing area) 3. Type of development (New residential/new industrial area/new mixed use area/existing residential/existing industrial/existing mixed use area) 4. Slope of the area (hilly area/High slope area/ mild slope area/complex terrain/Flat) 5. Number of connecting point 6. Approximate length of existing network (m) (not required if client chooses investigation for new area) 7. Approximate length of proposed line (m) (not required if client chooses investigation for existing area) 8. Existing Population Data ((not required if client chooses new area) 9. Projected population data (not required if client chooses existing area) 10. Existing VA (dwg) 11. LSO Network (dwg) (not required if client chooses investigation for existing area) 12. Rainfall data (if client can not provide, SMHI data can be used) 13. Surface Elevation/3d surface (if client can not provide, SCALGO data can be used) 14. Profile of pipe (dwg) 15. Pump data (no. of pump, hourly flow rate of pump, model number of pump, drawing of pump house) 16. Location of existing air valve and status of air valve (not required if client chooses investigation for new area) 17. Hourly Flow data from treatment plant (if any) | 1. Investigation PM 2. Sewer network plan map in GIS (PDF)

## ham-1
Rate | Base Amount in SEK/hr | PM (SEK/hr) | External Meeting (SEK/hr) | Duration | Main tasks | Data requirement | Deliverable
less than 0.5 ha | 4500 | 5000 | 6000 | 2-3 weeks | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
0.5 ha to 1 ha | 5000 | 5000 | 6000 | 2-3 weeks | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
1-3 ha | 6000 | 8000 | 6000 | 3-6 weeks | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
3-5 ha | 7500 | 8000 | 6000 | 3-6 weeks | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
5-10 ha | 9000 | 10000 | 6000 | 6-9 weeks | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
10-20 ha | 9000 | 10000 | 6000 | 2-3 months | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
20-30 ha | 10000 | 15000 | 6000 | 3-4 months | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
30-50 ha | 10000 | 15000 | 6000 | 4-6 months | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
50-75 ha | 11000 | 20000 | 6000 | 6-9 months | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
75-100 ha | 12500 | 25000 | 6000 | 9-12 months | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)
>100 ha | 14000 | 40000 | 6000 | Minimum 1 year | 1. Preparation of pipe network layout and definition 2. Water consumption calculation 3. Model setup 4. Hydraulic analysis 5. Water hammer simulation and transient flow analysis 5. Proposed solution | 1. Project location 2. Project area 3. DEM/Elevation data/Height model/VG of pipes and junctions 4. Existing water distribution network 5. Water connection points and existing pressure 6. Information on water sources (overhead tanks/reservoirs/water treatment plants) 7. Existing and projected population data 8. Information on existing pump 9. Existing and proposed landuse (i.e. residential areas, school. Market, industrial areas etc.) | 1. Investigation PM 2. Schematic drawings (GIS/CAD)